## Slide 1
KHIT ZAY
Strategic Expansion Plan
Multi-Vendor
Marketplace
Expansion
Strategy
Transforming Myanmar's e-commerce landscape by leveraging a 30-year legacy.
Prepared By
KHIT ZAY Strategy Team
March 10, 2026
Parent Company Context
Blazon MM Group
30-Year Legacy
17 Int'l Brands
1M+ Active Users
"From a single-vendor powerhouse to Myanmar’s premier curated marketplace—connecting lifestyle seekers with trusted sellers."
Complement, Don't Compete
Filling portfolio gaps with non-competing categories.
Quality-First
Rigorous vetting to maintain premium positioning.
Phased Scale
Controlled expansion from pilot to full launch.
Data-Driven Ops
Leveraging analytics for inventory and fulfillment.

## Slide 2
Starting Position
Active Customer Base
1,000,000+
International Brand Portfolio
17 Brands
Operational Legacy
30 Years
Building on a solid foundation of trusted logistics and customer service infrastructure established by Blazon MM Group.
Strategic Vision
Marketplace Scale
60-80
Quality Sellers
Product Volume
6,000+
Active SKUs
Financial Target
6.75B
Projected GMV (MMK)
Customer Experience
4.5/5
CSAT Score
Seller Value Proposition
Go-To-Market Phases
12-Month Success Metrics
Immediate Access: Direct reach to 1M+ active user base
Zero Risk: No upfront fees, commission-based model
Full Support: End-to-end logistics & customer service
Marketing Power: Integrated into established digital campaigns
Executive Summary
Strategy Overview
Expansion Roadmap
"To build Myanmar's premier curated marketplace by extending fashion & beauty leadership into complementary lifestyle categories."
1
Foundation
M 1-2
2
Pilot
M 3-4
3
Expand
M 5-7
4
Full Launch
M 8-12

## Slide 3
Target Categories (Yangon-Based)
Focus: Lifestyle Extension
PRIORITY
Watches
Casio, Seiko, Fossil. Premium authorized dealers.
LUXURY
Fragrances
Niche & designer perfumes above mass market.
TECH
Gadgets
Earbuds, smartwatches, power banks (<2kg).
Accessories
Sunglasses, jewelry, belts, wallets.
Home & Wellness
Aromatherapy, candles, small decor.
More categories in
Phase 4
Qualification Standards
Physical Presence
Yangon warehouse/office mandatory
Authenticity Guarantee
100% original with documentation
Fulfillment Capacity
Min. 50 orders/month capability
Liability Insurance
Required for items > 500k MMK
Strict Vetting Process
Execution Timeline & Milestones
PHASE 1: FOUNDATION
"Building the Rails"
Key Actions
Legal framework (SLAs)
Shopify Multi-vendor setup
Shortlist 50-100 sellers
MONTH 1-2
PHASE 2: PILOT
"Proof of Concept"
Targets
8% Comm.
10-15
Sellers
300
Orders/Mo
MONTH 3-4
PHASE 3: EXPANSION
"Controlled Growth"
Targets
Sellers:
30-50
Products:
1.5k - 3k
Fulfillment:
≥ 96%
MONTH 5-7
PHASE 4: FULL SCALE
"Market Leadership"
Year 1 Goal
80
Sellers
4k
Orders/Mo
MONTH 8-12
Seller Acquisition Strategy
"Complement, Don't Compete"
Phased Expansion
12-Month Roadmap

## Slide 4
Fixed Monthly Costs
MMK 2.15M
Platform & Tech Stack
690,000
Personnel (Mgmt + CS)
1,140,000
Ops & Marketing
315,000
Variable per Order
Avg. MMK 10,500
Delivery
2,250 - 3,750
Processing
2.9% + 450
Packaging
450
Insurance
1.5% (>150k)
Commission Strategy
8%
Pilot Phase (M 1-4)
Incentivize early adoption
12%
Standard Rate (M 5+)
Base platform fee
Volume Incentives (Month 9+)
Bronze
12%
Silver
10%
Gold
8%
12-Month Profitability Projection
Comparing Commission Revenue vs. Total Operational Costs
Revenue
Fixed Costs
Total Costs
Break-Even Point
215
orders / month
Requires approx. 4 orders per seller (at 60 sellers)
Avg. Gross Profit
MMK 10,000
Target Month
Month 9
Profitability Scenarios
Premium Watch
Price: 225k | Vol: 25
+ MMK 311k
Net Profit
Cheap Gadget
Price: 37.5k | Vol: 100
- MMK 270k
Net Loss
Financial Model
Path to Profitability & Unit Economics
Monthly Break-Even
~215 Orders
Year 1 GMV Target
MMK 6.75B

## Slide 5
Core Operational Workflow
Seller Onboarding
Application & Doc Submission
Business & Authenticity Vetting
Platform Training (Mandatory)
Portal & API Credentials
Product Management
Standardized Listing Upload
QA Review (Image 1200px+)
Real-time Inventory Sync
Low Stock Auto-Alerts
Order Fulfillment
Auto-routing to Seller
Seller Confirm (< 24h)
KHIT ZAY Standard Pack
Pickup & Real-time Track
CS & Returns
Omni-channel Support
Centralized RMA Portal
Seller Inspection (48h)
Refund Credit (3-5 Days)
Delivery Service Level Agreement (SLA)
Benchmark: 95% On-Time
Yangon Region
1-2 Days
Same-day express available
Major Cities
2-3 Days
Mandalay, Naypyidaw
Nationwide
3-7 Days
Rural Townships
Logistics Partners
J&T
J&T Express
Primary Partner (Nationwide)
DHL
DHL eCommerce
High-Value / Premium
EMS
Myanmar Post
Rural Reach
Operational Framework
End-to-End Workflow & Service Standards
Fulfillment Target
98% Success
CSAT Goal
4.5 / 5.0
1
2
3
4

## Slide 6
Critical Success Factors
Quality Over Quantity
Strict vetting ensures premium positioning and avoids "flea market" perception.
Leverage Infrastructure
Utilize Blazon's established logistics to lower barrier to entry for sellers.
Phased Growth Gates
Go/No-Go decisions at each phase based on strict financial & operational KPIs.
Risk Mitigation Strategy
Risk: Seller Quality Drop
High
Probationary pilot periods, "Mystery Shopper" audits, and performance reserves.
Risk: Logistics Failure
Med
Multi-carrier redundancy (J&T + EMS) and automated tracking integration.
Risk: Cash Flow
Med
Conservative commission modeling and phased marketing spend.
Strict Seller SLA Requirements
Non-compliance leads to account review
24h
Order Confirmation
48h
Max Dispatch Time
98%
Fulfillment Rate
<5%
Return Rate Cap
Year 1 Success Metrics Dashboard
Annual GMV Target
6.75 Billion MMK
Target Achieved @ Month 12
CSAT Score
4.5 / 5.0
Seller Retention
85%
Implementation Roadmap
Risk Mitigation & Success Metrics
Year 1 Status
Full Launch
Active Sellers
Target: 80+